## Traceability Matrix
Traceability Matrix
Prototype Title: | The Iron Keep
Scope: | The Iron Keep is a first-person puzzle game where a medieval warrior escapes an enemy keep by solving two puzzle rooms and defeating a guardian enemy.
Bitbucket Repository Link: | https://github.com/cmiele-snhu/The-Iron-Keep
Class | Functionality | Implementation Description | Program | Begin Phase | Complete Phase | Assigned to | Completed? Y/N | Notes
Player Character | Movement | Implement WASD movement, mouse look, spacebar jump, and E/LMB interact using axis and action input events in UE5 project settings. | Unreal Engine 5 | Alpha | Alpha | Self | Yes
Player Character | Physics Pickup | Implement a physics grab mechanic on LMB that lets the player pick up, carry, and throw physics objects. This mechanic is used in both puzzle rooms and the boss fight. | Unreal Engine 5 | Alpha | Alpha | Self | Yes
Player Character | Health System | Implement a health variable and damage system. Taking damage from the guardian or hazards reduces health. Health hitting zero triggers the game over screen. | Unreal Engine 5 | Alpha | Alpha | Self | Yes
Boss | Guardian (Turret) | A stationary turret guardian fires projectiles at the player. Player must use cover in the arena to avoid damage and throw physics pickup objects at the turret to deal damage. Turret cannot be damaged by direct player attacks. | Unreal Engine 5 | Alpha | Alpha | Self | Yes
Boss | Boss Defeat | Player defeats the turret guardian by throwing physics pickup objects at it. Physics objects deal damage on hit. When turret health reaches zero the exit unlocks. | Unreal Engine 5 | Alpha | Alpha | Self | Yes
Game | Win Condition | Guardian being defeated triggers the exit to unlock and displays the win screen. | Unreal Engine 5 | Alpha | Final Submission | Self | Yes
Game | Lose Condition | Player health reaching zero displays the game over screen with options to restart or return to the main menu. | Unreal Engine 5 | Alpha | Alpha | Self | Yes
Game | Timer & Code Format | All timed events use Timer nodes instead of Tick events. All game logic is inside appropriate classes with level sequences kept separate. | Unreal Engine 5 | Alpha | Final Submission | Self | Yes
Level | Level Layout | Block out the full level including starting cell, Room One, Room Two, and boss arena. Level should flow naturally without mechanically guiding the player. | Unreal Engine 5 | Alpha | Alpha | Self | Yes
Level | Environmental Puzzle (Room One) | Player breaks destructible boxes scattered around the room to find physics pickup items. Each item has an enum type. Player must try placing different items on two pressure plates simultaneously to find the correct combination that opens the door. Wrong items do nothing. | Unreal Engine 5 | Alpha | Alpha | Self | Yes
Level | Timed Puzzle (Room Two) | Player has 30 seconds after entering the room to find the correct physics pickup from several scattered around the room and place it on the pressure plate to open the door to the boss arena. Timer starts on trigger volume overlap. If timer hits zero the puzzle resets and pickups return to start positions. | Unreal Engine 5 | Alpha | Alpha | Self | Yes
Level | Boss Arena | Build the boss arena with cover objects the player can hide behind to avoid turret fire, and physics pickup objects scattered around for the player to throw at the turret. | Unreal Engine 5 | Alpha | Alpha | Self | Yes
UI | Player Health | Display player health in the upper left corner of the screen using a HUD widget. | Unreal Engine 5 | Alpha | Alpha | Self | Yes
UI | Game Timer | Display a game timer in the upper right corner counting up from zero. | Unreal Engine 5 | Alpha | Alpha | Self | Yes
UI | Objective Tracker | Display active objective text on screen that updates each time an objective is completed. | Unreal Engine 5 | Alpha | Alpha | Self | Yes
UI | Countdown Timer | Display a countdown timer during the Room Two timed puzzle. Timer starts when player enters the trigger volume at the room entrance. Turns red below 10 seconds. | Unreal Engine 5 | Alpha | Alpha | Self | Yes
UI | Win/Lose Screens | Display win and lose screens at the end of the game with options to restart or return to the main menu. | Unreal Engine 5 | Alpha | Final Submission | Self | Yes
Code | Code Comments | All blueprints must be commented explaining what each section does. | Unreal Engine 5 | Alpha | Final Submission | Self | Yes
Repository | Feature Branching | Create branches based on the feature being worked on. Merge via pull requests when features are complete. Commits labelled properly. | Github | Alpha | Final Submission | Self | Yes

## Test Plan
Test Plan
Bitbucket Repository Link: | [Insert Bitbucket Link]
Test Feature | Description of Test | Pass/Fail | Bugs | Runtime Errors | Updates/Error Resolution
Example: Pickup interaction | Example: Implement print strings to ensure player input is firing and appropriate events are being called. Display class name on interaction via print string to ensure the correct class is interacting. | Example: Fail | Example: Pickup interaction functions, but integer doesn't increment properly. | Example: Accessed None when trying to read Pickup_BP | Example: Verify item interaction is setting the Pickup_BP references variable properly. An issue here may be why the variable cannot be accessed by the editor.
Player Movement | Test WASD movement, mouse look, jump, and interact input. Use print strings to confirm axis and action events are firing correctly. | Pass | Line trace debug line was visible in game during play. | None | Set Draw Debug Type to None on Line Trace By Channel node in BP_PlayerChar. Debug line no longer visible in game.
Physics Pickup | Pick up and drop a physics object. Confirm item raises and moves with the player on interact and drops properly on release. | Pass | Throw function was dropping the object instead of launching it with force. | None | Added Add Impulse node after INT_Drop call using Camera forward vector multiplied by 2000. Objects now launch correctly in the direction the player is facing.
Environmental Puzzle (Room One) | Break boxes in Room One to find items. Try placing wrong items on both plates and confirm door stays closed. Place correct items on both plates and confirm door opens. Remove one item and confirm door closes. | Pass | Second door was not opening even though both plates had correct pickups. bIsRoomTwo branch was not falling through to door logic on the False pin. | None | Connected both True and False pins of bIsRoomTwo branch into the door logic chain so both Room One and Room Two buttons correctly trigger their respective doors.
Timed Puzzle (Room Two) | Enter Room Two and confirm 30 second countdown starts. Find and place correct pickup on plate within time and confirm door opens. Let timer expire and confirm puzzle resets with pickups returning to start positions. | Pass | Timer restarted every time the player re-entered the trigger volume. Timer also kept running after the correct pickup was placed on the plate. | None | Added bTimerStarted boolean to Level Blueprint to prevent timer from restarting on re-entry. Added OnPuzzleSolved event dispatcher on BP_Button bound to StopCountdown in Level Blueprint. Timer stops correctly when puzzle is solved.
Guardian Turret | Confirm turret fires projectiles at the player. Confirm player takes damage when hit. Move behind cover and confirm projectiles are blocked. Confirm turret cannot be damaged by direct player interaction. | Pass | Turret was shooting in the general direction of the player but not accurately hitting them. | None | Projectile Movement Component was using the actor forward vector instead of the pivot rotation. Added Get Component by Class to get the Projectile Mover and Set Velocity using the Pivot forward vector multiplied by 2000. Projectiles now aim correctly.
Boss Defeat Condition | Throw physics objects at the turret and confirm damage is applied each hit. Confirm defeat condition fires and exit unlocks when turret health hits zero. | Pass | Turret was dying in 3 hits instead of 4. Physics pickups were double hitting due to multiple collision components on the turret. | None | Added bHasHit boolean to BP_PhysicPickup to block multiple hit registrations per throw. Also removed Simulation Generates Hit Events from the statue mesh, keeping it only on the Cube component. Turret now correctly takes 4 hits to defeat.
Player Health & Damage | Take damage from guardian and hazards and confirm health decreases. Confirm game over screen triggers when health hits zero. | Pass | Health bar binding was dividing by zero on game start because MaxHealth defaulted to 0. | None | Set MaxHealth default value to 100.0 in BP_PlayerChar. Health bar displays correctly from game start on re-test.
Win Condition | Defeat the guardian and confirm the win screen displays. | Pass | Win screen was not appearing after turret was destroyed. | None | Added Create Widget and Add to Viewport for win widget in BP_PhysicPickup On Component Hit when turret health hits zero. Added Set Game Paused to freeze game on win.
Lose Condition | Let health reach zero and confirm the game over screen displays with restart and main menu options. | Pass | Lose screen was not triggering on timer expiry, only on player death. | None | Added Create Widget and Add to Viewport for lose widget in both BP_PlayerChar Take Damage and Level Blueprint CountdownTick. Both conditions now correctly show lose screen and pause game.
UI - Health Display | Confirm health bar displays in upper right and updates correctly when damage is taken. | Pass | None. | None | No fix needed.
UI - Game Timer | Confirm game timer displays and counts up from zero on game start. | Pass | Timer was not incrementing, stayed at 0:00 the whole game. | None | Event Tick in WBP_HUD was setting ElapsedTime to Delta Time directly instead of adding to it. Fixed subtraction node to ElapsedTime + DeltaTime. Timer counts up correctly on re-test.
UI - Objective Tracker | Confirm objective text updates when each objective is completed. | Pass | None. | None | No fix needed.